## Website_Audit_SEO_Action_Tracke
ID | Date Added | Category | Priority | Status | Page / Area | File Name | File Path | Issue / Opportunity | Recommended Action | Reason / Expected Benefit | Estimated Difficulty | Estimated Time | Dependencies | Assigned To | Date Completed | Notes
1 | 2026-04-27 | Technical SEO | Critical | Not Started | Free Installation Estimate | estimate.html | /estimate.html | Page contains two <h1> tags (lines 366 and 382). Search engines treat this as a structure error and split keyword authority. | Demote the second <h1> to <h2>. Keep the primary H1 as 'Get Your Free Installation Estimate' or strengthen with location. | Single-H1 pages signal one main topic to Google. Fixing avoids a structural penalty. | Easy | 15 min | None | Developer |  | Quick fix â€” verify visually after change to confirm typography stays correct.
2 | 2026-04-27 | Conversion | Critical | Not Started | Reviews | reviews.html | /reviews.html | Page is 100% placeholder copy. Six review cards say '[REPLACE THIS WITH A REAL REVIEW]'. AggregateRating + Review schema is commented out waiting for real data. | Collect 5â€“10 real Google / HomeStars reviews with permission. Replace placeholders. Uncomment AggregateRating + Review schema. Wire up to Google Business Profile if possible. | Social proof is the single biggest local-SEO + conversion lever. Rich-result review stars in SERP add 30â€“50% CTR. No real reviews = no review-snippet eligibility. | Medium | 3â€“4 hr | Need real reviews from owner | Owner + Marketer |  | Owner must provide review text + permission. Marketer formats and inserts.
3 | 2026-04-27 | Conversion | Critical | Not Started | Contact form | contact.html | /contact.html | Form submission uses a mailto: link in JavaScript handleSubmit() â€” opens user's email client. No backend persistence; data is lost if user closes browser. No success/failure feedback. | Replace mailto: with a proper form handler â€” Formspree / Basin / Netlify Forms / Resend.com. Add success and error states. Optionally store in a Google Sheet via webhook. | Email-based form is unreliable and unprofessional. Lead loss rate likely 40â€“60% on this form. | Medium | 1â€“2 hr | Sign up for form-handler service | Developer |  | Free tiers exist (Formspree 50/mo). Fastest fix: Netlify Forms if hosting moves to Netlify.
4 | 2026-04-27 | Performance | High | Not Started | Homepage | about-section-picture.svg | /about-section-picture.svg | 8.1 MB SVG file embedded on homepage. SVGs that large usually contain raster image data â€” defeats the purpose of vector format. | Open in editor and either re-export as optimized SVG (under 200 KB) OR convert to JPG/WebP at 80% quality. Update any references. | Single 8 MB asset can dominate page-weight on slow connections. Reducing to <300 KB removes a Lighthouse performance flag. | Easy | 30 min | Need design source (Illustrator / Figma) OR raster fallback | Developer |  | Compress with svgo or open in Inkscape and re-save. If SVG was meant to be a photo, just convert to JPG.
5 | 2026-04-27 | Local SEO | High | Not Started | Service-area expansion | (new) sprinkler-service-markham.html | /sprinkler-service-markham.html | Markham (~330k residents) is the largest unaddressed market adjacent to current service area. No dedicated page; only referenced in homepage areaServed schema. | Create new service-area page following the established template (use sprinkler-service-aurora.html as scaffold). Localize for Markham â€” Angus Glen / Unionville / Cornell / Markham Village neighborhoods, soil characteristics, demographics. | Largest single SEO win available. Markham searches outvolume all current cities combined. | Medium | 4 hr | None | Developer + Marketer |  | Add to sitemap.xml after launch. Cross-link from Richmond Hill area page (adjacent).
6 | 2026-04-27 | Content SEO | High | Not Started | Spring Sprinkler Opening | (new) sprinkler-service-spring-opening.html | /sprinkler-service-spring-opening.html | Spring opening is a flagship $90 service buried inside sprinkler-systems.html. Aprilâ€“May search volume in Ontario is significant. No dedicated landing page. | Create dedicated page with: pricing, what's included (re-pressurization, leak inspection, zone test, controller programming), booking deadline urgency (mid-April rush), Ontario-specific timing (last frost guidance). | Captures high-intent seasonal queries. Direct revenue: each spring opening = $90 + likely repair/upgrade upsells. | Medium | 3 hr | None | Marketer + Developer |  | Cross-link from homepage seasonal section + every area page.
7 | 2026-04-27 | Content SEO | High | Not Started | Fall Winterization | (new) sprinkler-service-fall-winterization.html | /sprinkler-service-fall-winterization.html | October winterization is mentioned in blog and FAQ but has no dedicated landing page. Same opportunity as Spring Opening on the inverse seasonal cycle. | Create dedicated page mirroring the Spring Opening structure â€” pricing, low-pressure compressor brand callout, freeze-damage cost statistics, October booking urgency. | Captures fall search demand. Reduces inbound phone-tag (people searching 'winterization near me' land on a converting page). | Medium | 3 hr | None | Marketer + Developer
8 | 2026-04-27 | Content SEO | High | Not Started | Sprinkler Repair | (new) sprinkler-systems-repair.html | /sprinkler-systems-repair.html | Repair is a year-round high-intent search ('sprinkler repair near me'). Currently a sub-section of sprinkler-systems.html â€” gets none of the search authority a dedicated page would. | Create dedicated page with common issues (stuck valves / broken heads / wet spots / no pressure / zone failure), diagnostic checklist, same-day guarantee callout, $95 mobilization explanation, AI-Smart-Intake first-hour-free hook. | Same-day repair queries are highest-converting in irrigation. Dedicated page captures the search and routes to booking. | Medium | 3 hr | None | Marketer + Developer
9 | 2026-04-27 | Conversion | High | Not Started | Landscape Lighting | landscape-lighting.html | /landscape-lighting.html | Page sells a visual-first product but has zero installed-system photos. Only generic benefit icons (ðŸ¡ âœ¨). Buying decision needs visual proof. | Add 8â€“12 before/after photo gallery of installed lighting projects. Native HTML grid (no plugin). Each photo with location + brief description. | Visual proof is the #1 conversion driver for landscape lighting. Estimated +15â€“25% conversion lift. | Medium | 4 hr | Need real project photos | Owner + Marketer |  | Owner must provide photos. Hire photographer to shoot 5â€“10 evening installations if needed.
10 | 2026-04-27 | Schema | High | Not Started | Blog posts | All blog-*.html | /blog-*.html | Only 1 of 9 blog posts has BlogPosting schema (spring-sprinkler-opening). Other 8 posts have only basic WebPage / NewsArticle markup with no datePublished / author / dateModified. | Add complete BlogPosting JSON-LD to each blog post: @context, @type, headline, datePublished, dateModified, author (Patrick), publisher (PJL), image, articleSection. | Enables Google Search blog rich-results, author E-E-A-T signal, publication-date badges in SERP. Cumulative authority signal across the blog. | Easy | 1.5 hr (all posts) | None | Developer |  | Use existing post as template; vary headline / date / image per post.
11 | 2026-04-27 | Technical SEO | High | Not Started | Legal pages | privacy-policy.html, terms-of-service.html, accessibility-statement.html | /privacy-policy.html, /terms-of-service.html, /accessibility-statement.html | All three legal pages lack OG / Twitter / JSON-LD metadata. Inconsistent with rest of site (89% coverage). | Add OG title / OG description / OG image / Twitter Card tags. Add minimal WebPage @type JSON-LD with isPartOf reference. | Consistency for crawlers and social-share previews. Low-traffic pages but completes the site's schema profile. | Easy | 30 min | None | Developer
12 | 2026-04-27 | Content SEO | High | Not Started | Meta descriptions | sprinkler-service-newmarket.html, sprinkler-service-aurora.html, blog-spring-fertilization-sprinkler-timing-gta.html, blog-landscape-renovation-sprinkler-prep-gta.html, blog-tree-irrigation-newmarket-gta.html | /sprinkler-service-*.html, /blog-*.html | 5 pages have meta descriptions over 160 chars (max useful display width). Newmarket page is 319 chars â€” truncates badly in SERP. Aurora 308 chars. | Trim each to 140â€“155 chars. Move neighborhood lists or detail to body content. Lead with the local hook + service + a benefit. | Truncated descriptions look unprofessional and lose CTR. Tight descriptions consistently outperform long. | Easy | 45 min | None | Marketer
13 | 2026-04-27 | Content SEO | High | Not Started | Title strength | contact.html, estimate.html, quote.html, faq.html | /contact.html, /estimate.html, /quote.html, /faq.html | Titles are weak / generic. 'Contact Us' instead of 'Contact PJL Land Services â€” Newmarket Sprinkler Experts'. Missing keywords. | Rewrite each title to include primary keyword + location + brand. Stay 50â€“60 chars. | Generic titles cost SERP CTR and waste keyword authority. Strong titles are free SEO. | Easy | 30 min | None | Marketer |  | Update <title> | og:title | twitter:title for each page.
14 | 2026-04-27 | Internal Linking | High | Not Started | Blog posts | All blog-*.html | /blog-*.html | No 'Related services' or 'Book this service' CTAs at the end of blog posts. Reader has no path from how-to content to the service that performs it. | Add a 'Related services' card group at the end of each post linking to relevant service-page(s) + a primary CTA button (Get a Quote / Book Service Call). | Blog content currently has zero conversion path. Adding these can lift blog-source bookings 5â€“10x without adding traffic. | Easy | 1 hr | None | Marketer |  | Each post should link to 2â€“3 services + 1 area page where geographically relevant.
15 | 2026-04-27 | Internal Linking | High | Not Started | Service pages | sprinkler-systems.html, landscape-lighting.html | /sprinkler-systems.html, /landscape-lighting.html | Service pages don't link out to the 5 area pages. A homeowner from Richmond Hill landing on sprinkler-systems gets no signal that there's a localized page for them. | Add a 'Service Areas' section on each core service page with linked tiles for Newmarket / Aurora / King City / Richmond Hill / Vaughan (and Markham once built). | Improves internal-link equity to area pages â€” and reassures local prospects they're in coverage. | Easy | 30 min | None | Developer
16 | 2026-04-27 | Conversion | High | Not Started | Quote vs Estimate | estimate.html, quote.html | /estimate.html, /quote.html | Two near-identical conversion pages. Quote.html has the excellent interactive builder. Estimate.html is older / form-based. Users get split between funnels with no clarity which to use. | Decide canonical conversion path. Suggest: keep quote.html as the universal builder; convert estimate.html to a redirect OR re-purpose for landscape-lighting-specific estimates only. Update all CTAs to use one consistent label. | Reduces decision friction. Funnels traffic to the highest-converting flow. | Easy | 1 hr | Owner decision | Owner + Developer |  | Brand-tone preference: 'Estimate' is honest / no-pressure. 'Quote' is more commercial. Consider keeping 'Get a Free Estimate' label but routing to the builder.
17 | 2026-04-27 | Maintainability | High | Not Started | Repository hygiene | audit-*.png, postfix-*.png, about-debug-*.png, about-home-*-check.png, about-tablet-*-after.png, about-phone-*-after.png, Home-estate.png, Home-large.png, Home-small.png, Same Day Service.svg | /various | ~28 MB of working-set / dev-iteration screenshots and unused assets sit at the project root. They are not referenced in any HTML but ship with the repo and may end up in a GitHub Pages deploy. | Move to a /dev-archive/ folder OR add to .gitignore + delete. Verify each is unreferenced before removing. | Cleaner repo, faster clones, smaller deploy. Reduces confusion for future maintainer. | Easy | 30 min | None | Developer |  | Run grep across all .html for each filename before deleting to confirm unreferenced.
18 | 2026-04-27 | Local SEO | Medium | Not Started | Service-area expansion | (new) sprinkler-service-stouffville.html | /sprinkler-service-stouffville.html | Stouffville (~35k residents) is east of Aurora â€” newer estate properties with high lighting/irrigation demand. Currently no page. | Create following the area-page template. Localize for Whitchurch-Stouffville: Lakeside Hideaway / Wheler Mills / acreage market / new estates. | Expands eastern service coverage without overlap. Likely lower competition than Markham. | Medium | 3 hr | None | Marketer + Developer
19 | 2026-04-27 | Local SEO | Medium | Not Started | Service-area expansion | (new) sprinkler-service-east-gwillimbury.html | /sprinkler-service-east-gwillimbury.html | East Gwillimbury (~35k) is between Aurora and Stouffville. Already in homepage areaServed schema; needs a dedicated page. | Create using template. Localize for Sharon / Holland Landing / Mount Albert / Queensville. | Low-effort win. Schema already mentions; just needs the page to back the claim. | Medium | 3 hr | None | Marketer + Developer
20 | 2026-04-27 | Local SEO | Medium | Not Started | Service-area expansion | (new) sprinkler-service-thornhill.html | /sprinkler-service-thornhill.html | Thornhill (~80k) is technically inside Vaughan but is searched as a distinct neighborhood with high lighting demand and affluent demographics. No dedicated page. | Create page with landscape-lighting positioning emphasized (premium homes / mature landscapes / curb-appeal focus). | Captures lighting-specific Thornhill searches that the broader Vaughan page diffuses. | Medium | 3 hr | None | Marketer + Developer
21 | 2026-04-27 | Content SEO | Medium | Not Started | Smart Controllers | (new) hydrawise-installation.html | /hydrawise-installation.html | Hydrawise / smart-controller is a strong differentiator but lives only as a sub-section. 'Hydrawise installer' + 'smart sprinkler controller' searches are loyal high-AOV. | Create dedicated page with: Hydrawise feature deep-dive (weather-based scheduling / remote app / water-savings ROI), retrofit process, pricing ($380â€“$520), Hunter University / Authorized Installer credentials. | Captures retrofit market (existing-system owners). Larger TAM than new-build only. | Medium | 2.5 hr | None | Marketer + Developer
22 | 2026-04-27 | Content SEO | Medium | Not Started | Drip Irrigation | (new) drip-irrigation.html | /drip-irrigation.html | Drip irrigation is in the homepage schema and Patrick's bio but has no content. Growing category for vegetable gardens / perennials / water-conscious landscaping. | Create page covering use cases (vegetables / trees / ornamental beds), benefits (targeted / mulch-friendly / per-plant), pricing, and how it integrates with Hydrawise. | Diversifies offering beyond lawn irrigation. Lower competition keyword. | Medium | 2.5 hr | None | Marketer + Developer
23 | 2026-04-27 | Conversion | Medium | Not Started | Warranty page | (new) warranty.html | /warranty.html | 3-year warranty is mentioned scattered across schema / area pages / estimate page. Deserves dedicated page documenting coverage / claim process / exclusions. | Create page with: clear coverage table (parts / labour / span), claim process steps, exclusions, comparison to industry-standard 1-year. | Major trust signal. Above-industry warranty is a competitive differentiator that's currently invisible. | Easy | 2 hr | None | Marketer
24 | 2026-04-27 | Conversion | Medium | Not Started | Process / How It Works | (new) process.html | /process.html | No page documents the install-to-finish customer journey. Reduces buyer hesitation when prospects can see exactly what to expect. | Create 'How It Works' page outlining steps for sprinkler install: free consultation â†’ on-site assessment â†’ custom design â†’ install day â†’ walk-through â†’ ongoing service. Same for landscape lighting. | Reduces uncertainty for first-time buyers. Particularly helpful for higher-ticket lighting projects. | Easy | 2 hr | None | Marketer
25 | 2026-04-27 | Conversion | Medium | Not Started | Pricing Guide | (new) pricing.html | /pricing.html | Pricing is partial / scattered ($90 spring opening / $585+$525-per-zone install / $245-per-fixture lighting). A pricing landing page would capture buyer-research traffic. | Create page with: 'Starting at' pricing for each service / what drives the price / typical project ranges / what's included. Include disclaimer that on-site visit calibrates final number. | High-intent traffic. Reduces unqualified leads (people calling who can't afford). Trust signal â€” most competitors hide pricing. | Medium | 2 hr | Owner approval on pricing transparency | Owner + Marketer |  | Owner must approve which numbers go public.
26 | 2026-04-27 | Content SEO | Medium | Not Started | Cost blog post | (new) blog-sprinkler-system-cost-ontario.html | /blog-sprinkler-system-cost-ontario.html | 'How much does a sprinkler system cost in Ontario / GTA' is one of the highest-volume sprinkler queries. No matching content currently. | Write 1500â€“2000 word post: cost factors / lot size / soil / zone count / brand / warranty value / typical budget tiers ($2.8kâ€“$12k+). End with quote-builder CTA. | Highest-volume single keyword in irrigation searches. Single best blog post you could publish for SEO. | Medium | 2 hr | None | Marketer |  | Pair with 'Get a quote' CTA at bottom.
27 | 2026-04-27 | Content SEO | Medium | Not Started | Seasonal blog post | (new) blog-when-to-turn-on-sprinklers-ontario.html | /blog-when-to-turn-on-sprinklers-ontario.html | Aprilâ€“May Ontario search spike for 'when to turn on sprinklers'. No matching content currently. | Write seasonal-timing post: last frost date by region (Newmarket / Aurora / GTA), soil temp readiness, ground-frost checklist. Link to Spring Opening service. | Captures urgent seasonal traffic. Drives spring-opening bookings. | Easy | 1.5 hr | None | Marketer
28 | 2026-04-27 | Content SEO | Medium | Not Started | Maintenance blog post | (new) blog-sprinkler-maintenance-checklist.html | /blog-sprinkler-maintenance-checklist.html | No homeowner-facing maintenance checklist currently. Authority + email-capture opportunity (downloadable PDF). | Write checklist post: spring prep / mid-season / fall prep. Each task with DIY-vs-professional threshold. Offer PDF download for email capture. | Builds authority. Email capture for newsletter (future re-marketing). | Medium | 1.5 hr | Email-capture form (mailing list service) | Marketer
29 | 2026-04-27 | Local SEO | Medium | Not Started | Bylaws blog post | (new) blog-watering-bylaws-york-region.html | /blog-watering-bylaws-york-region.html | Each York Region municipality has different watering rules. Homeowners search 'watering restrictions Newmarket / Aurora / Vaughan' frequently. No matching content. | Write municipality-by-municipality bylaw table: Newmarket / Aurora / Richmond Hill / Vaughan / King City / Markham / Stouffville. Position Hydrawise as automatic-compliance. | Strong local-authority signal. Gets linked to / referenced by other local sites. Captures niche local searches. | Medium | 1.5 hr | Verify current bylaws | Marketer |  | Bylaws change. Add a 'last verified' date and review yearly.
30 | 2026-04-27 | Internal Linking | Medium | Not Started | Footer service-area links | All pages | style.css + per-page footer | Footer service-area links exist but don't include all five area pages on every page. Inconsistent across the site. | Standardize footer service-area block: all current + future area pages. Centralize into a single source if a static-site generator is adopted (see ID 60). | Stronger sitewide internal linking. Easier for crawlers to discover all area pages. | Easy | 30 min | None | Developer
31 | 2026-04-27 | Performance | Medium | Not Started | Image lazy-loading | All pages with below-fold images | /various .html | Only 9 of ~105 images use loading='lazy'. Below-fold images load in the critical path unnecessarily. | Add loading='lazy' to every <img> below the first viewport. Keep eager loading on hero images only. | Cuts mobile data usage. Improves Largest Contentful Paint (LCP). | Easy | 1 hr | None | Developer
32 | 2026-04-27 | Performance | Medium | Not Started | Responsive image sizing | homepage-hero.jpg, landscape-lighting-hero.jpg, sprinkler-installation.jpg, spring-fall-service.jpg | /various | Hero images are served at full resolution to all devices regardless of viewport. No <picture> or srcset. | Generate 3 sizes per hero (mobile 768w / tablet 1280w / desktop 2000w) and use srcset with sizes attribute. Or use CSS image-set() for backgrounds. | Mobile users currently download desktop-size images. Lighthouse flag. | Medium | 2 hr | Image processing tool (already have Pillow) | Developer
33 | 2026-04-27 | Maintainability | Medium | Not Started | CSS breakpoint consolidation | style.css | /style.css | 11 distinct media-query breakpoints across the site (1024 / 1000 / 900 / 880 / 768 / 760 / 720 / 640 / 600 / 540 / 520 / 480). Some redundant. | Consolidate to 4 core breakpoints: 1024 (desktop) / 768 (tablet) / 640 (large mobile) / 480 (mobile). Audit and merge overlapping rules. | Easier to maintain / fewer surprises when adjusting layouts. Reduces mistakes when one breakpoint is updated and similar ones aren't. | Hard | 4â€“6 hr | None | Developer |  | Major refactor â€” should be done with full visual regression check across all pages and breakpoints.
34 | 2026-04-27 | Maintainability | High | Not Started | Nav / footer duplication | All 28 .html files | /various | Navigation block (~110 lines) and footer (~100 lines) are duplicated across all 28 HTML files. Any change requires 28 edits â€” high error rate / drift risk. | Migrate to a static-site generator (Astro / 11ty / Hugo) with shared partials. Alternative low-effort fix: server-side include via a build-time concat script. | Single biggest maintainability win. Future-proofs the site for whoever maintains it after the current owner. | Hard | 1â€“2 days | None | Developer |  | Astro is recommended for this stack: keeps the static-output / no-server simplicity but adds component reuse.
35 | 2026-04-27 | Schema | Medium | Not Started | FAQPage schema for new service pages | Spring Opening / Fall Winterization / Repair pages (when built) | /various | FAQPage schema is excellent on existing area pages and faq.html. New service pages should match. | Add FAQPage JSON-LD with 3â€“5 service-specific questions to each new service page (cost / timing / DIY-risk / warranty / process). | FAQ rich-results in SERP. High-CTR snippet style. | Easy | 30 min per page | Service pages must exist | Developer
36 | 2026-04-27 | Schema | Low | Not Started | BreadcrumbList schema | Service-area pages | /sprinkler-service-*.html | Visible breadcrumb UI exists but no BreadcrumbList JSON-LD. Misses the rich-result eligibility. | Add BreadcrumbList to each area page: Home â†’ Service Areas â†’ [City]. | Helps Google understand hierarchy. Breadcrumb in SERP. | Easy | 15 min per page | None | Developer
37 | 2026-04-27 | Schema | Low | Not Started | AggregateRating preparation | index.html | /index.html | Once 5+ verified reviews are live (see ID 2), homepage should expose AggregateRating. Currently absent. | Add AggregateRating JSON-LD with ratingValue / reviewCount once reviews are live. Update reviewCount monthly. | Star rating in local-pack and SERP. Major CTR lift. | Easy | 30 min | Depends on ID 2 (reviews live) | Developer |  | Don't fake / inflate. Manual penalty risk.
38 | 2026-04-27 | Accessibility | Low | Not Started | Mobile nav button | nav.js + nav HTML in all pages | /various | Hamburger button has no aria-expanded attribute. Screen readers can't announce open/closed state. | Add aria-expanded='false' (toggled to 'true' on open) to .nav-hamburger. Add aria-controls pointing to .nav-mobile id. | WCAG compliance. Screen reader users currently can't tell if menu is open. | Easy | 15 min | None | Developer
39 | 2026-04-27 | Accessibility | Low | Not Started | Footer social links | All pages with footer | /various | Footer social-icon links contain only a single character (e.g., 'f' for Facebook). Screen readers read 'f link'. | Add aria-label='Facebook' / aria-label='Instagram' / etc. to each social link. Or wrap visible text in <span class='visually-hidden'>. | Screen reader accessibility. Common WCAG fix. | Easy | 15 min | None | Developer
40 | 2026-04-27 | Accessibility | Low | Not Started | Decorative SVG marking | All pages | /various | Decorative inline SVG icons (logo-mark / etc.) lack aria-hidden='true'. Screen readers may announce them. | Add aria-hidden='true' to all decorative SVG sprites used as icons. | Cleaner screen-reader experience. WCAG-A polish. | Easy | 30 min | None | Developer
41 | 2026-04-27 | Brand Tone | Low | Not Started | Reviews page tone | reviews.html | /reviews.html | Page uses generic phrasing ('takes 30 seconds') that drifts from the brand's honest / non-pushy voice. | Rewrite intro and CTA copy in PJL's existing tone. Look at FAQ and About pages for tone reference. | Brand consistency = trust. Mismatched copy reads as templated / lazy. | Easy | 30 min | None | Marketer |  | Can be done at the same time as ID 2.
42 | 2026-04-27 | Brand Tone | Low | Not Started | Lighting page emoji density | landscape-lighting.html | /landscape-lighting.html | Page uses emoji icons heavily (ðŸ¡ ðŸ”’ ðŸŒ¿ âœ¨). Friendlier than the rest of the site but inconsistent with the professional / clean tone. | Replace emoji with the brand's existing inline-SVG icon system used on other pages (water drop / sparkle pattern in nav.html). | Visual consistency across pages. Inline SVGs render at any size and respect color tokens. | Easy | 1 hr | None | Developer
43 | 2026-04-27 | Conversion | Medium | Not Started | Homepage above-the-fold testimonial | index.html | /index.html | Homepage hero has CTA + value prop but no immediate social proof above the fold. | Add a single testimonial quote + name + rating beneath the hero â€” once real reviews are live (see ID 2). | First-impression trust. Most visitors don't scroll past the fold. | Easy | 30 min | Depends on ID 2 | Marketer + Developer
44 | 2026-04-27 | Conversion | Low | Not Started | Team photos | about.html | /about.html | Only Patrick is shown. If there's a crew, photos build trust and signal that bookings won't be solo-trader-overrun. | Add 1â€“2 photos of crew at work (with permission). Caption with first names. | Humanizes the company. Reassures buyers who worry the owner can't scale. | Easy | 1 hr | Owner provides photos | Owner + Marketer
45 | 2026-04-27 | Local SEO | Low | Not Started | Service-area expansion | (new) sprinkler-service-caledon.html | /sprinkler-service-caledon.html | Caledon (~70k) â€” northwestern GTA. Lower density / larger lots = higher avg project value. | Create page emphasizing estate-property positioning. | Premium-positioning play. Lower volume / higher AOV. | Medium | 3 hr | None | Marketer + Developer
46 | 2026-04-27 | Local SEO | Low | Not Started | Service-area expansion | (new) sprinkler-service-whitchurch-stouffville.html | /sprinkler-service-whitchurch-stouffville.html | Subset of broader Stouffville coverage. May be redundant with ID 18. | Decide if ID 18 covers this or build separately. | Geographic completeness. | Medium | 3 hr | Decision on ID 18 scope | Marketer |  | Probably skip if Stouffville page is comprehensive.
47 | 2026-04-27 | Local SEO | Low | Not Started | Service-area expansion | (new) sprinkler-service-innisfil.html | /sprinkler-service-innisfil.html | Innisfil already mentioned in FAQ as service area. Needs a dedicated page to back the claim. | Create page using template. Localize for Innisfil / Cookstown / Lefroy. | Schema-claim consistency. Captures Innisfil-specific searches. | Medium | 3 hr | None | Marketer + Developer
48 | 2026-04-27 | Content SEO | Low | Not Started | Backflow Testing | (new) backflow-testing.html | /backflow-testing.html | Patrick is licensed for backflow testing (mentioned in About bio + schema) but no service page captures this. | Create page explaining York Region requirements / cross-contamination basics / annual testing schedule / pricing. | Captures niche compliance traffic. High-trust signal (technical credential). | Easy | 1.5 hr | None | Marketer |  | Specialty service â€” likely lower volume but high authority.
49 | 2026-04-27 | Content SEO | Low | Not Started | Commercial irrigation | (new) commercial-irrigation.html | /commercial-irrigation.html | Schema mentions commercial properties but no commercial landing page. Likely 20%+ of revenue but invisible to commercial property managers searching. | Create page with commercial use cases (HOA / strip mall / multi-tenant residential / municipal). Mention of WSIB / liability insurance is a commercial trust signal. | Captures commercial / property-management traffic. Higher AOV. | Medium | 2 hr | Owner confirms commercial offer + pricing | Owner + Marketer
50 | 2026-04-27 | Content SEO | Low | Not Started | Frost-depth blog | (new) blog-sprinkler-frost-depth-ontario.html | /blog-sprinkler-frost-depth-ontario.html | 'How deep should sprinkler lines be buried' is a consistent search. No matching content. | Write technical post on Ontario / York Region burial-depth requirements. Link to install + winterization services. | Compliance-related authority signal. Solid mid-volume search. | Easy | 1.5 hr | None | Marketer
51 | 2026-04-27 | Content SEO | Low | Not Started | Brand comparison blog | (new) blog-hunter-vs-rainbird.html | /blog-hunter-vs-rainbird.html | 'Best smart sprinkler controller' is high-intent shopping. Currently Hydrawise-only message â€” comparison post defends choice without defensiveness. | Write Hunter Hydrawise vs Rain Bird ESP-Me feature / cost / support comparison. | Captures competitor-research traffic before they decide. | Easy | 2 hr | None | Marketer
52 | 2026-04-27 | Documentation | High | Not Started | Maintenance handoff doc | WEBSITE_MAINTENANCE_AND_SEO_HANDOFF.md | /WEBSITE_MAINTENANCE_AND_SEO_HANDOFF.md | No professional handoff documentation currently exists. If the owner steps away the site is undocumented. | Create comprehensive handoff doc (delivered as part of this audit). Maintain quarterly. | Continuity of operations. Future-proofing. | Medium | Created with this audit | None | Developer |  | Created 2026-04-27.
53 | 2026-04-27 | Documentation | High | Not Started | Implementation plan | SEO_IMPLEMENTATION_PLAN.md | /SEO_IMPLEMENTATION_PLAN.md | No phased SEO / content roadmap currently exists. | Create phased plan (delivered as part of this audit). | Roadmap for owner / future marketer. | Medium | Created with this audit | None | Marketer |  | Created 2026-04-27.
54 | 2026-04-27 | Documentation | Medium | Not Started | Action tracker CSV | Website_Audit_SEO_Action_Tracker.csv | /Website_Audit_SEO_Action_Tracker.csv | No central tracker for all open SEO / technical / content items. | Maintain this CSV as items are completed. Update Status / Date Completed columns. | Single source of truth for progress. | Easy | Ongoing | None | Owner / Marketer |  | This file. Update weekly.
55 | 2026-04-27 | Maintainability | Medium | Not Started | Inline-style cleanup | All pages | /various | Several inline style='...' attributes exist (footer link colors / stat font-size / skip-link absolute positioning). Should be class-based. | Replace with utility classes or component CSS in style.css. Remove inline styles. | Cleaner separation of concerns. Easier theme adjustments. | Easy | 1 hr | None | Developer
56 | 2026-04-27 | Performance | Low | Not Started | Google Fonts weight reduction | style.css | /style.css | Loads 14 weights of Barlow Condensed + DM Sans. Network cost ~80â€“120 KB. | Audit which weights are actually used in CSS. Drop unused weights from the @import URL. | Faster initial paint. Smaller font payload. | Easy | 30 min | None | Developer
57 | 2026-04-27 | Local SEO | High | Not Started | Google Business Profile | External (Google Business Profile) | N/A | Google Business Profile is the largest local-SEO factor. Status / completeness unknown to this audit (external system). | Owner: ensure GBP is verified / has hours / has 10+ photos / weekly posts / categories accurately set / reviews pursued. Add UTM-tagged links to website. | GBP drives 60â€“80% of local-pack visibility. Free. | Medium | 2â€“4 hr setup + ongoing | Owner access | Owner
58 | 2026-04-27 | Authority | Medium | Not Started | Citations & directories | External | N/A | Local citations on Yelp / HomeStars / TrustedPros / BBB / Yellow Pages / York Region Chamber etc. matter for local pack. | Audit current citation profile. Build out missing reputable directories. Ensure NAP (Name / Address / Phone) is consistent. | Citation consistency is a top-5 local-pack ranking factor. | Medium | 2â€“3 hr | None | Marketer |  | Tools like BrightLocal / Whitespark help. Or do manually for top 10.
59 | 2026-04-27 | Authority | Medium | Not Started | Backlink strategy | External | N/A | Link profile likely thin (small business / new site). Local-business backlinks accelerate ranking. | Pursue: York Region Chamber listing / local newspaper supplier directory / Hunter dealer locator / supplier (Hydrawise) website / charity sponsorships. | Authority signal. Compounds over time. | Hard | Ongoing | None | Marketer + Owner
60 | 2026-04-27 | Maintainability | Low | Not Started | Static site generator migration | Whole project | N/A | Plain HTML site is fine but maintenance scales linearly with page count. Once 30+ pages exist nav / footer changes are painful. | Migrate to Astro (recommended) â€” preserves static output / SEO friendly / shared components / Markdown blog. | Drastically improves maintainability. Speeds up future feature work. | Hard | 2â€“3 days | None | Developer |  | Major project. Wait until next major redesign or after 40+ pages.
61 | 2026-04-27 | Conversion | Medium | Not Started | Coverage / service map | (new) coverage-map.html OR section on contact.html | /various | No visual map showing service radius. Geographic clarity helps prospects self-qualify. | Embed Google Map with marked service area (or a stylized SVG map). Add to contact page or new dedicated page. | Reduces out-of-area inquiries. Visual trust. | Medium | 2 hr | Google Maps embed key (free) | Developer
62 | 2026-04-27 | SEO | Low | Not Started | Sitemap freshness | sitemap.xml | /sitemap.xml | Sitemap has '<lastmod>' values. These should update when pages are meaningfully changed. | After any major page change update lastmod. Ideally automate as part of a build script. | Helps Google know when to re-crawl. | Easy | Ongoing | None | Developer
63 | 2026-04-27 | SEO | Low | Not Started | Sitemap pending pages | sitemap.xml | /sitemap.xml | Comments at bottom of sitemap mention pending pages (winterization / commercial / gallery / additional area pages). When those pages are built they need to be added to sitemap.xml. | On launch of each new page from this tracker â€” append <url> entry to sitemap. Resubmit sitemap in Google Search Console. | Ensures crawl coverage. Without sitemap entry pages may take weeks to be indexed. | Easy | 5 min per page | Pages must exist | Developer
64 | 2026-04-27 | Local SEO | Medium | Not Started | NAP consistency check | All pages | /various | Name / Address / Phone should be byte-identical across the site and external citations. | Audit all 28 HTML pages and external listings (GBP / Yelp / etc.). Standardize on a single canonical NAP block. | Consistency is a ranking factor for local pack. | Easy | 1 hr | None | Marketer
65 | 2026-04-27 | SEO | Low | Not Started | hreflang for Quebec / FR market | All pages | /various | hreflang en-ca already set. If Patrick offers French-language service (Quebec / Ontarian francophones) consider FR variants. | Skip unless French-language market is a real opportunity. Otherwise leave as is. | Not currently applicable. | N/A | N/A | Owner decision | Owner |  | Likely not applicable. Documented for completeness.